## Sheet1
Product : APP KUBE |  | Date: 12-feb-2024
Module : Role
Test By : mohd niyaz ullah
BUG REPORT
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def_001 | Dropdown Box Not Closing After Selecting Policy in Role Creation | The dropdown box for selecting a policy does not close after selecting "All access" or "No access" when creating a new role in the AppKube application. | When creating a new role in the AppKube application and selecting a policy from the dropdown box, the dropdown box remains open even after the selection is made. This prevents users from easily moving to the next step in the role creation process, as the open dropdown box obstructs their view and interaction with other elements on the page. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to Role-Based Access Control. 7. On the same page, click on the "Role Module" section. 8. Click on the "Create New Role" button. 9. In the role creation form, click on the dropdown box for selecting a policy. 10. Select either "All access" or "No access" from the dropdown options. 11. Observe that the dropdown box remains open even after making the selection. | Low | Medium | Open | AppKube | https://ibb.co/Dk84FMB | The issue with the dropdown box not closing after policy selection affects the user experience and workflow during role creation. Implementing a fix to automatically close the dropdown box upon policy selection will improve usability and streamline the role creation process. | mohd niyaz ullah
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def_002 | Inability to Delete Selected Policy Sets | Users are unable to delete selected policy sets when prompted in the AppKube application. | When attempting to delete selected policy sets in the AppKube application, users encounter a problem where the deletion process fails to execute despite confirmation. After selecting the policy sets and clicking on the delete button, a confirmation prompt is displayed asking "Do you want to delete?" However, upon confirming the deletion by clicking "Delete," the action does not proceed, and the selected policy sets remain unchanged. This issue prevents users from effectively managing policy sets, potentially leading to clutter and confusion in the application's configuration. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to Role-Based Access Control. 7. Select the policy sets to be deleted. 8. Click on the delete button. 9. Confirm the deletion when prompted. 10. Observe that the selected policy sets are not deleted despite confirmation. | High | High | Open | AppKube | https://ibb.co/P61JLkL | The inability to delete selected policy sets impedes users' ability to manage access control effectively. A resolution is necessary to ensure proper functionality and usability of the application's policy management features. | mohd niyaz ullah
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def_003 | Missing Alert Message for Exceeding Character Limit in Role Description Field | Users are not alerted when exceeding the character limit in the role description field during role creation in the AppKube application. | When creating a new role in the AppKube application and entering text into the "Role Description" field, there is a character limit imposed on the input. However, when the user exceeds this limit, there is no alert message or indication provided to notify them of the constraint. As a result, users may inadvertently exceed the character limit without realizing it, leading to truncated or incomplete role descriptions. This issue diminishes user experience and may result in confusion regarding the proper length of role descriptions. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to Role-Based Access Control. 7. Click on the "Role Module" section. 8. Click on the "Create New Role" button. 9. Enter text into the "Role Description" field exceeding the character limit. 10. Observe that no alert message is displayed indicating the character limit has been exceeded. | Medium | Medium | Open | AppKube | https://ibb.co/tPzsFcX | The absence of an alert message for exceeding the character limit in the role description field hinders user awareness and may lead to unintended consequences such as truncated or incomplete role descriptions. Implementing an alert message will improve user experience and prevent confusion. | mohd niyaz ullah
Defect ID | Bug Title | Bug Summary | Bug Description | Step to replicate | Severity | Priority | Status | Product | Attachments | Remark | Reported By | Assigned to
Def_004 | Incorrect Button Label "Edit" Instead of "Update" When Editing Role | The button label remains as "Edit" instead of changing to "Update" after modifying a role in the AppKube application. | When editing a role in the AppKube application and making changes to its settings or description, the button label for saving the changes remains as "Edit" instead of updating to "Update." This inconsistency in button labeling may cause confusion for users, as they may expect the button to reflect the action of updating the role with the changes made. Instead, the button label remains the same as when initially accessing the edit mode, potentially leading to user errors or misunderstandings regarding the purpose of the button. | 1. Log in to the AppKube application. 2. Navigate to the dashboard. 3. Click on the setting icon. 4. Navigate to the admin page. 5. Click on "User and Permission." 6. Navigate to Role-Based Access Control. 7. Click on the "Role Module" section. 8. Create a new role or select an existing role to edit. 9. Click on the three dots menu from the left side of the role. 10. Select "Edit Role" from the popup options. 11. Modify the role settings or description. 12. Observe that the button label remains as "Edit" instead of changing to "Update" to reflect the action of saving the changes. | Low | Medium | Open | AppKube | https://ibb.co/mXYXg8Q | The inconsistency in button labeling when editing a role may lead to user confusion or misunderstanding of the action performed. Updating the button label to "Update" will enhance clarity and usability of the application's interface. | mohd niyaz ullah